## SpC 3.12
Licence number and name: |  | SpC 3.12 Capital Projects
Ofgem contact: |  | Jonathan Farrier
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Assigned to | Due Date | Response | Issue closed?
1 | 30.10.2020 | SGN | 3.12.4 | The risk associated with the definition of outputs against the EJP creates a major issue. Clarity is required on how this will be assessed against the detail contained in EJP. The reduction stated is to Zero. It should be modified to allow for a more proportionate reduction to the deemed non delivery. |  | Ofgem | December | The description of outputs in Appendix 1 have been amended. | Closed
2 | 30.10.2020 | SGN | 3.12.2 | The Special Condition defines the output only as a reference to the EJP. The EJP contains detail from within the conceptual design. However, this detail will inevitably change as we progress towards the detailed and 'for construction' designs. SGN is therefore 'at risk' if the full content of a very detailed EJP is used as a reference. The customer benefit is realised if the intervention and the system clearly defined. For example, a REPLACEMENT of the GAS PRE-HEATING SYSTEM. However, the NARMs methodology goes even further by defining a monetary risk benefit for the intervention on the asset system, which represents the benefit to the customer. NARMs values are available for almost all projects with the exception of the following: Scotland T8: Pitcairngreen to Huntingtower - R04 and R05 (capacity), E&I upgrade programme (5 sites), ICMDL, Telemetry upgrades (8 offtakes), Dreghorn (capacity), E&I upgrade programme (4 sites), New PRS (Edinburgh South East Wedge) (capacity), Telemetry upgrade programme (73 PRS), Tranent (capacity) Metering uncertainty programme (6 sites), Southern E&I upgrade programme (2 sites), ICMDL, Telemetry upgrade programme (2 offtakes) E&I upgrade programme (23 sites), East Morden (Capacity), Telemetry upgrade (82 PRS), Wavendon (Capacity), Metering uncertainty programme (1 site), Note: the E&I projects detailed above are large programmes where the expenditure per site is small. These do not warant being included as an PCD. Note: 5 capacity projects included as PCD have only been generally defined within the EJP and these should be retained as specific intervention types on specific asset systems. | It is recommended that the references to the EJP in appendix 1 are replaced with the full NARMs risk benefit as at 31st March 2026 with the exception of projects listed (E&I to be excluded, capacity to be referred to by the intervention type and relevant system). | Ofgem | December | The description of outputs in Appendix 1 have been amended. | Closed
3 | 30.10.2020 | SGN | Definitions | The term 'delivery' is somewhat undefined in this context | should be defined as 'the commissioning or recommissioning into service of an asset after the stated intervention has been delivered'. | Ofgem | December | The description of outputs in Appendix 1 have been amended to make them clearer. | Closed
4 | 29.10.2020 | Cadent | 3.12.2a | Reference is made to 'date' the draft determination states in the Gas Distribution Annex p72 that 'expected timing of delivery is end of RIIO-GD2'. This renders the data surplus to requirement, or allows it to be defined as end of period. Other, in period, dates have not been suggested by ofgem for gas distribution. | remove 'delivery dates ' replace with '31st March 2026' | Ofgem | December | This is one of several possible drafting approaches, we have preferred the one in our proposed modifications. | Closed
5 | 29.10.2020 | Cadent | 3.12.5 | Reference is made to 'date' the draft determination states in the Gas Distribution Annex p72 that 'expected timing of delivery is end of RIIO-GD2'. This renders the data surplus to requirement, or allows it to be defiend as end of period. Other, in period, dates have not been suggested by ofgem for gas distribution. | remove 'delivery dates ' replace with '31st March 2026' | Ofgem | December | This is one of several possible drafting approaches, we have preferred the one in our proposed modifications. | Closed
6 | 29.10.2020 | Cadent | 3.12.6 | As written will recover 100% of funding for partial as well as full non delivery. This is not proportionate. See response to draft determination GDQ22/23. | remove 'in order to reduce the allowance for the output to zero.' and replace with 'in order to reduce the allowance for the output proportionally'. | Ofgem | December | Drafting has been amended so this is an evaluative PCD to reflect our Final Determinations position. Please see Final Determinations for our decision on this policy. | Closed
7 | 29.10.2020 | Cadent | 3.12.6 | As per our response to Kelvin Hui, on 10th September 2020, on the PCD Policy Document we do not believe that our Capital Projects should be Mechanistic PCDs. We believe they should be Evaluative PCDs, where they pass a materiality threshold of 0.5% of annual base revenue, as this will ensure that we can innovate and continue to engage stakeholders on the solutions used to deliver the outputs. Where they do not exceed a materiality threshold of 0.5% of annual base revenue a baseline allowance should be provided. |  | Ofgem | December | Drafting has been amended so this is an evaluative PCD to reflect our Final Determinations position. Please see Final Determinations for our decision on this policy. | Closed
8 | 29.10.2020 | Cadent | 3.12.8 | Offtakes & PRS Metering should not be included in the PCD for Cadent, they are part of the NARMs approach. This is therfore a 'double count'. See our response to DD GDQ22/23 | remove Offtakes and PRS Metering from Appendix 1 | Ofgem | December | This point relates to the policy in question, please see Final Determinations for our decision on this policy. | Closed
9 | 29.10.2020 | Cadent | 3.12.8 | We note SGN also has a large number of items in the PCD which should instead be part of NARMs | removes SGNs NARMs outputs from Appendix 1 | Ofgem | December | This point relates to the policy in question, please see Final Determinations for our decision on this policy. | Closed
10 | 29.10.2020 | Cadent | 3.12.8 | The allowances will need to be aligned to the values in FD. We have provided feedback to Ofgem that some of the values put forward in DD are not correct. |  | Ofgem | December | This point relates to the policy in question, please see Final Determinations for our decision on this policy. | Closed
11 | 29.10.2020 | Cadent | 3.12.8 | The items listed in Appendix 1 should be expanded for Cadent to include the Lowestoft Project (APP_CAD_09.63) and HP Valves APP_CAD_09.64. See our response to DD Cadent Q5 |  | Ofgem | December | This point relates to the policy in question, please see Final Determinations for our decision on this policy. | Closed
12 | 29.10.2020 | Cadent | 3.12.7 | Reference is made in this section to 3.12.5, is this a typo, should it infact be 3.12.6 | Replace '3.12.5' with '3.12.6' | Ofgem | December | Drafting amended to correct cross-reference. | Closed
13 | 29.10.2020 | Cadent | 3.12.8 | States 'the Regulatory Years to which those values relate' this text is not required, the delivery date for all items is 31st March 2026. As such phasing of allowance or spend is not relevent | remove 'the Regulatory Years to which those values relate' | Ofgem | December | This is one of several possible drafting approaches, we have preferred the one in our proposed modifications | Closed
14 | 29.10.2020 | Cadent | 3.12.8 | The inclusion of Offtakes & PRS Metering in this PCD for Cadent, whilst is forms part of NARM for other GDNs, is contradictory to the policy set out in the NARMs methodology. Para 1.22 of the NARM annex to Ofgem's Final Determinations states: "For the GD sector, the Baseline Allowances associated with NARM remain subject to update between the publication of Final Determinations and the implementation of RIIO-GD2. This is to ensure that the final targets we set for GDNs accurately reflect the decisions we have made at Final Determinations, including ensuring a consistent approach is taken across GDNs as to which assets are included within the NARM." This work needs to be removed from this PCD to ensure consistency across GDNs of which assets are included in NARM. If they are not this would impose a disadvantage on Cadent compared to all other GDNs. | remove Offtakes and PRS Metering from Appendix 1 | Ofgem | February | This point relates to the policy in question, please see Final Determinations for our decision on this policy. | Closed
15 | 22.1.2021 | Cadent | Appendix 1 | Lowestoft number is quoted as 2.27 and should be 2.29 as per Cadent appendix and EJP | Correct the number | Ofgem | February | EJP states £2.27m, so we not believe this is an error and £2.27m is the correct value. For Reference, please see the document titled 'Appendix 09.6 - Lowestoft Harbour' attached to the Cadent_SQ_CA_45a' response. | Closed
16 | 19.01.2021 | ENWL | (Licence consultation para 6.6) | This para suggests that a Full PCD Review will be required in all cases except Fully Delivered. Suggest this is expanded include fully delivered by alternative solution. The Authority may still request a Full Report under the first part of the clause | …… to undertake a Full PCD Review in all cases except those where the PCD is Fully Delivered or Fully Delivered with Alternative Specification | Ofgem | February | ENWL are actually referring to the Draft PCD Reporting Methodology document that was published as an AD to the licence back in December. This comment will be addressed as part of the final PCD methodology document, rather than here. | Closed
17 | 19.01.2021 | SGN | Appendix 1 | Change to outputs associated with R02 Dunkeld | Construct a new pressure reduction station at Dunkeld and a new IP main from the pressure reduction station to the outlet of Logierait PRS. Abandon the at risk elements of the existing steel HP pipeline from Dunkeld to Logierait and install a new district governor to receive gas from the new IP pipeline. | Ofgem | February | We have accepted an amended version of this proposed clarification to the project description. | Closed
18 | 19.01.2021 | SGN | Appendix 1 | Change to outputs associated with T8: Pitcairngreen to Huntingtower - R04 and R05 | Reinforce the Pitcairngreen to Huntingtower pipeline (supplying Huntingtower PRS) by installing a new pipeline and facilities to allow the new pipeline to be inline inspected. | Ofgem | February | Accept clarification to the description of the project output. | Closed
19 | 19.01.2021 | SGN | Appendix 1 | We propose a change to the currently defined outputs associated with our E&I Upgrade Programme to not be site specific. Being tied into a specific site could lead to a worse consumer outcome should a site not listed require unforeseen attention in GD2 that was not at the time of the business plan submission. By quantifying the number of sites and type of sites, it will enable the flexibility to deliver a better customer outcome if justified from an engineering point of view whilst maintaining the integrity of the PCD. We also propose a change to this text as it important to note that the whole work programme includes a mixture of required work at each of the sites. For example Site A will only require an electrical upgrade, whereas Site B may require an electrical upgrade and some instrumentation replacements. This was explicit within our EJP. | Change to output to state: The full, or partial, upgrade of the required electrical, instrumentation and control assets at SGN Offtakes and PRS sites: Offtake sites Sc: 5 Sites So: 2 Sites PRS sites Sc: 4 Sites So: 23 Sites | Ofgem | February | Accept clarification to the description of the project output. | Closed
20 | 19.01.2021 | SGN | Appendix 1 | Change to outputs associated with Newton Mearns and Waterfoot PRS | Change to output to state: Decommission the existing Newton Mearns PRS and Waterfoot PRS. Construct a new PRS and new outlet pipework to connect the Newton Mearns Grid and Waterfoot Grid. | Ofgem | February | Accept clarification to the description of the project output. | Closed
21 | 19.01.2021 | SGN | Appendix 1 | Change to outputs associated with Provan PRS | Full site rebuild of Provan PRS (Beardmores and City), replace above ground pipework (HP, MP, and Local MP) with buried pipelines, and install facilities to allow the new pipeline to be inline inspected. | Ofgem | February | Accept clarification to the description of the project output. | Closed
22 | 19.01.2021 | SGN | Appendix 1 | Change to outputs associated with Mappowder | Replace the pre-heating system and pressure control system at Mappowder NTS offtake. | Ofgem | February | Accept clarification to the description of the project output. | Closed
23 | 19.01.2021 | SGN | Appendix 1 | Change to outputs associated with [REDACTED] The license wording specifies the material and route of lay solution in detail and is too specific, it does not allow for any engineering difficulties found during design or construction of the project. As this is an evaluative PCD which will be subject to an independent report at completion, the license wording "The main will be replaced with a new high-density polyethylene pipeline under the river" requires changing to 'a new replacement supply will be constructed 'which allows flexibility in construction but delivers the target output of this PCD . | Output = Decommission a 434m section of 12” steel intermediate pressure main located within the bridge structure and service tunnel. The existing main will be replaced with a suitable and fit for purpose alternative | Ofgem | February | Accept clarification to the description of the project output. | Closed
24 | 19.01.2021 | SGN | 3.12.6 | The licence should clearly define if this is an Evaluative or Mechanistic PCD. In this case Evaluative. | Proposed text "3.12.6 The Authority will, in accordance with the Evaluative PCD as set out within the PCD Reporting Requirements and Methodology Document, consider …….” | Ofgem | February | This is one of several different valid drafting approaches and we have chosen the one set out in our licence modifications. | Closed