## SpC1F
Licence number and name: |  | SpC 3.23 Domestic Connections Volume Driver
Ofgem contact: |  | Jonathan Farrier
No. | Date raised | Comment from | Reference (Part X, Para Y) | Cross Sector/Finance Tracker Reference | Comment | Suggested alternative drafting | Assigned to | Due Date | Response | Issue closed?
1 | 30.10.2020 | SGN | Reference Para 10.49 – 10.50 |  | We are comfortable with the principle of the licence but are unable to make further comment until we have visibility of the ex-anti unit rates to be incorporated. |  | Ofgem |  | This point relates to the policy in question, please see Final Determinations for our decision on this policy. | Closed
2 | 30.10.2020 | SGN | SpC 3.23 |  | We have concerns around financing as ex-anti unit rates are still to be proposed. |  | Ofgem |  | This point relates to the policy in question, please see Final Determinations for our decision on this policy. | Closed
3 | 29.10.2020 | WWU | Appendix Tables |  | We think having one price for each network is better than several. Splitting by mains diameter ignores the fact of different pressure tiers. The table needs to clarify that the cost table is for the net cost of the connection (the element funded by WWU). If two prices are going to be used the table needs to show <=180mm and >180mm currently it misses out 180mm. | Amend title of each table in the appendix by adding "funded by network" as follows "Distribution Network specific matrix costs (£ per Domestic Connection funded by network....." In tables delete lines "<180mm" and ">180mm" and have one price for each network. | Ofgem |  | We have set one unit cost per network (one for mains and one for services). The licence draft now makes clear that the cost is the non-recoverable (net) cost. The table doesn't need to be updated because there is only a single unit cost now. | Closed
4 | 29.10.2020 | Cadent | n/a |  | How will the volume driver operate in terms of settlement - annually in arrears, mid and end of PCD term or all end of term? Are there any other specific data collection requirements to support the reopener other than number of connections per diameter band and unit cost per network? In our EJP we detailed requirements for unauthorised connections - would these be dealt with under the same arrangements or do these need to be identified separately? |  | Ofgem |  | The volume driver will follow the default approach of annual updates through the AIP in arrears. The volume driver will not separately account for unauthorised connections. Data collection will be managed through the RRP. Tables yet to be developed, but will include at least gross cost, net cost, volume of mains and services at various diameter bands and property/connection types. | Closed
5 | December Consultation response | WWU | Appendix 1 |  | Ofgem to check the GDN values as we are unable to reconcile for the Mains to the figure in the Licence. | Ofgem to consider comment | Ofgem | February | Ofgem has responded to this issue through the FDQ process. | Closed
6 | December Consultation response | WWU | Appendix 1 |  | We require separate values to be published for existing housing and new housing as these better reflect changes in workload and have a closer link to the allowances that GDN has for those activities. | Ofgem to consider comment | Ofgem | February | This relates to a difference in opinion about the policy, our policy decision is set out in FDs. | Closed
7 | December Consultation response | WWU | 3.15.3 |  | Term VMt is meant to relate to mains to new and existing housing only | Insert the words "delivered to new and existing housing" so that it reads "means the length of Mains commissioned in kilometres across all diameter bands delivered to new and existing housing" | Ofgem | February | Accept clarification to the definition of the VMt term. | Closed
8 | 2021-01-04 | Cadent | Appendix 1 -KM of mains commissioned |  | EoE states 8.5 and Cadent annex states 8.6 | Amend to reflect annex | Ofgem | February | This table in the licence has been removed. | Closed
9 | 2021-01-04 | Cadent | Appendix 1 -KM of mains commissioned |  | NW states 5.5 and Cadent annex states 5.6 | Amend to reflect annex | Ofgem | February | This table in the licence has been removed. | Closed
10 | 2021-01-04 | Cadent | Appendix 1 -no of service connections commissioned |  | EoE states 39395 and Cadent annex states 39394 | Amend to reflect annex | Ofgem | February | This table in the licence has been removed. | Closed
11 | 2021-01-04 | Cadent | Appendix 1 -no of service connections commissioned |  | NW states 14690 and cadent annex states 14689 | Amend to reflect annex | Ofgem | February | This table in the licence has been removed. | Closed
12 | 2021-01-04 | Cadent | Appendix 1 -no of service connections commissioned |  | WM states 12375 and cadent annex states 12736 | Amend to reflect annex | Ofgem | February | This table in the licence has been removed. | Closed
13 | 2021-01-16 | Cadent | 3.15.3 |  | We cannot confirm that this formula will adjust revenues correctly, and as intended by Ofgem’s Final Determinations, due to the absence of guidance notes for the PCFM handbook. As such, our ability to undertake an informed assessment of this licence condition is limited |  | Ofgem | February | The formula has been rechecked and updated. | Closed
14 | 2021-01-16 | Cadent | Appendix 1 |  | There are errors in the unit costs shown in this licence condition. We have submitted queries and evidence on these errors through the Final Determination Question (FDQ) process. The assessment and correction of these errors form part of Ofgem’s errata process and the inclusion of incorrect unit costs within this licence condition impacts and limits our ability to undertake an informed assessment through this licence consultation. |  | Ofgem | February | Ofgem has responded to this issue through the FDQ process. | Closed
15 | December Consultation response | SGN | Appendix 1 |  | The unit cost comparison against the other GDNs has been challenged under SGN_FDQ_019 due to large variance. |  | Ofgem | February | Ofgem has responded to this issue through the FDQ process. | Closed