## SpC 3.28
Licence number and name: |  | SpC 3.28: Intermediate Pressure Reconfigurations PCD
Ofgem contact: |  | Graham Dickson/Callum Mayfield
No. | Date raised | Comment from | Reference (Part X, Para Y) | Comment | Suggested alternative drafting (if necessary) | Assigned to | Due Date | Response | Issue closed?
1 | 2021-01-19 | SGN |  | This formula has not changed from being input led, it measures the output of the quantity of RPI and Service governors. This is a mechanistic PCD and therefore should measure how many of the 515 IP services have been decommissioned and a new supply installed to the emergency control valve. At the point of submission this project was based upon a feasibility study of a number of outline designs, this formula, does not deliver value for the customer as it drives the behaviour to install the full quantity of RPI and services governors even if designs offer a more efficient approach. As a point to note, this license formula has been incorrect from the outset, it omits any allowance for mains and services, and continues to refer to steel mains for replacement, which is not the case. This project as described in the EJP’s consisted a mix of 9.32km <180mm PE new lay and reconfigured PE main. It is intended that at locations where multiple IP services are in close proximity to one another small PRI’s are utilised to provide a small low pressure system which is constructed from new lay PE mains. For single properties, it is proposed to relocate the IP service governor to a location greater than 3m from the building line to affect this relocation associated PE main would also be required. |  |  |  | Drafting amended | Closed
2 | 2021-01-19 | SGN |  | The FD formula allowance is incorrect also, within FD SGN Annex (page 21 table 24) a baseline of £3.68m has been allowed and footnote 19 states "SGN noted that the mains and services requiring replacement are steel and not iron therefore our suggestion in Draft Determinations that this was already funded under the Tier 1 mains and services PCDs was incorrect. It also set out that it could not fund this under the Iron pipes >30mm and steel pipes, including associated services EJP, as suggested in our QEM outcome as the proposed workload wasn’t granted at the time of our Draft Determinations." although in the FD formula appendix tables (1&2) only £2.3m has been allowed for the quantity of RPI and Service governor. |  |  |  | Drafting amended | Closed
3 | 2021-01-19 | SGN | 3.28.5 | The PCD formula needs to be changed to be based on the output that is delivered - the number of IP services that are reconfigured. Currently the formula is based on the quantity of small PRIs and number of service governors which is the engineering solution anticipated at the time of the business plan submission, rather than the output ‘IP Service reconfigurations’ that we are delivering. | The formula should be adjusted to IPRR(t) =IPSR(IPST – IPSD).10_6 Where IPSR means the unit cost of each IP Service Reconfiguration IPST means the target of number of IP Service Reconfigurations IPSD means the number of IP Service Reconfigurations |  |  | Drafting amended | Closed
4 | 2021-01-19 | SGN | Appendix 1 | The allowances detailed in Appendix 1 are incorrect. | Intermediate Pressure configurations should have an annual cost of 736,000 and total allowance of £3,680,000 |  |  | Drafting amended | Closed
5 | 2021-01-19 | SGN | Appendix 2 | The unit costs detailed in Appendix 2 are incorrect. The target installation number should be annualised with assoicate unit costs. | Target number of IP Service Reconfiguration should have an annual number of 103 per year and 515 in total and unit cost of £7,146 |  |  | Drafting amended | Closed