## NZARD Re-opener
Licence number and name: |  | Special Condition 3.5 Net Zero and Re-opener Development Fund use it or lose it allowance
Ofgem contact: |  | Mo Khalif (GD GT), Joseph Slater (ET)
No. | Date raised | Comment from | Reference (Part X, Para Y) | Summary of comment | Suggested alternative drafting (if necessary) | Response | Issue closed?
1 | 2021-03-16 | Cadent | Para. 2.7 | Adding reference to Local Area Energy Plans to underscore their importance (as with the NZR) | Add bullet in 2.7 before "Associated customer and stakeholder engagement": Local Area Energy Planning | We have adopted the suggested wording | Closed
2 | 2021-03-16 | Cadent | Para 2.9 | Would help add flexibility if 2.9 also referenced using the pre-construction and small projects re-opener to requets a general increase in the NZARD UIOLI allowance. | In 2.9, change last sentence: "…...can request additional costs through the re-opener submission for that project, or for the overall allowance, though approval of such requests will not be guaranteed and will be subject to the re-opener." | This fund is fixed and companies may not ask for an increase of the UIOLI fund. Companies may, however, use the re-opener where they anticipate the £1m materiality threshold will be reach. | Closed
3 | 2021-03-16 | WWU | General | Missing sections on provision for the governance and administration of the fund & will include a definition of allowable and unrecoverable expenditure (as per special condition 3.5.8) | Add these sections to the final document | We have amended our document to make it clear what constitutes as 'allowable RDF expenditure'. Upon revisiting what we have said the licence, we no longer think 'unrecoverable expenditure' was appropriate or necessary to define and we will consider removing the licence text as part of any future licence changes. | Closed
4 | 2021-03-16 | WWU | General | Note that special condition 3.5.11 states that the authority will direct an amendment to the value of RDFR where it considers a UIOLI is appropriate which raises questions around the processes used to trigger the assessment and funding decision | It is their view "that final process must enable swift decision-making, provide 28 days for representation to be made regarding the determination and enable revenue recovery timelines to be as short as possible" | This specifically relates to the process we will follow if we think we need to recover parts of the UIOLI - not where we are directing further funds. The whole of this fund has already been given to companies in baseline funding. | Closed
5 | 2021-03-16 | WWU | General | Clarification sought over whether allowance of £0.95m is a 5 year (enabling a large project of £2m if necessary) or 1 year allowance? |  | We have added further clarification to the final version of the document to confirm the allowance is for the duration of the price control, and no 'per year' split applies. | Closed
6 | 2021-03-16 | Renewable UK Cymru | General | Specifically the UIOLI should be developed in collaboration with industry to facilitate a simple, uniform approach and that governance structures must include provision for coordinating engagement of stakeholders. |  | We have been working closely with the industry in workshops on the processes and tools we will use across the net zero mechanisms we've designed for RIIO-2 and will continue to do so as we recognise the sentiment expresed in this comment. | Closed
7 | 2021-03-16 | Renewable UK Cymru | General | The £2m cap, with option to apply for further funding through the re-opener does little to ensure more complex projects can be planned properly. | Allow an interim assessment to allow funding to be recovered through subsequent reopeners, whether or not the project goes ahead. | As per our Final Determination, one of the reasons we created this pot was to provide companies with upfront funding for preparatory work and less material projects. This fund, alongside the agile Net Zero Pre-construction and Small Projects Re-opener, we believe, strikes the right balance and allows for companies to gain access to funding appropriately. | Closed
8 | 2021-03-16 | Renewable UK Cymru | General | Regard to the degree of risk for projects which intended to apply under MSIP but are established as LOTI projects and ensuring they do not breach the £2m cap. Allowing the NZARD to be accessible for pre-FEED work on LOTI projects |  | The process for LOTI projects to seek PCF funding (both in baseline allowances and through re-openers) is well established and does not need to be included here.
9 | 2021-03-16 | National Grid | General | Document should be titled the Net Zero and Re-opener Development Fund Governance Document and refer to the "Net Zero and Re-opener Development Fund use it or lose it allowance" throughout |  | We have ensured uniform naming throughout. | Closed
10 | 2021-03-16 | National Grid | General | The words “as if it formed part of their licence” should be deleted from the cover page while making clear that SC 3.5 is the “NZARD Licence Condition” as, for instance, referred to in the review section on page 4. |  | We have removed "as if it formed part of their licence". We have also defined NZARD Licence Condition. | Closed
11 | 2021-03-16 | National Grid | Context Section | In the context section refer instead to a DN Operator and the NTS Operator as such terms are each defined in standard special condition A3 of the GT licence. |  | We have updated text to ensure reference to the correct licensees and licences throughout. | Closed
12 | 2021-03-16 | National Grid | 1.4 | Clarify as per FD document that, given there are no specific outputs set and a delivery date of 26 March 2026, there is no restriction when the NZARD can be used | Suggest an additional paragraph (1.4) to confirm that the total allowances set out in para. 1.3 are available to be spent over the price control period rather than on a five-year split basis and that any UIOLI adjustment will accordingly look at spend across the price control period as a whole not on a regulatory year basis. | We have added further clarification to the final version of the document to confirm the allowance is for the duration of the price control, and no 'per year' split applies. | Closed
13 | 2021-03-16 | National Grid | Costs | SC 3.5.8 contemplated providing definitions for allowable and unrecoverable RDF expenditure | Update to define these terms | We have amended our document to make it clear what constitutes as 'allowable RDF expenditure'. Upon revisiting what we have said the licence, we no longer think 'unrecoverable expenditure' was appropriate or necessary to define and we will consider removing the licence text as part of any future licence changes. | Closed
14 | 2021-03-16 | National Grid | General | GT: Is the £2m cap for whole project expenditure or early development only? | Clarify - 2.5 states NZARD shouldn’t be used for capital projects expected to cost more than £2m and 2.9 states that early development work should not exceed £2m per project. | That's correct. Both have a cap of £2m. | Closed
15 | 2021-03-16 | National Grid |  | Include the LOTI reopener for pre-FEED, as this is potentially precluded under the current FD but these type of NZ projects are more likely to need this type of expenditure | Eligible reopeners set out in para. 2.8 should be expanded to include the Large Onshore Transmission Investment (LOTI) reopener for projects >£100m, | The process for LOTI projects to seek PCF funding (both in baseline allowances and through re-openers) is well established and does not need to be included here. | Closed
16 | 2021-03-16 | National Grid | General | Does Chapter 3 represent the required reporting obligations as per SC 3.5.8c? | If so, this should be confirmed in 3.1 and that no other bespoke reporting will be required | We have added text to clarify the additional requirements beyond the formal RIGs. | Closed
17 | 2021-03-16 | National Grid |  | MSIP: Please refer to Special Condition 3.14 of the ET licence |  | We have adopted the suggested change. | Closed
18 | 2021-03-16 | National Grid | General | The use it or lose it allowance is provided for / set out on the face of the licence as a result of the 3/2/21 Authority direction. It would be more accurate in this definition to refer to the allowance set out in Special Condition 3.5 (and replicated in Chapter 1 of this guidance). |  | We have adopted the suggested change. | Closed
19 | 2021-03-16 | National Grid | General | Net Zero re-opener: Please refer to the re-opener provided for in Special Condition 3.6. |  | We have adopted the suggested change. | Closed
20 | 2021-03-16 | Scottish & Southern |  | Given need for flexibility and uncertainty, add a general condition which allows expenditure on other activities which network companies can reasonably evidence have been undertaken to help facilitate the delivery of projects under the net zero-related re-openers |  | The licence condition already includes a definition that captures "any other relevant necessary activities to progress to final investment decision" | Closed
21 | 2021-03-16 | Scottish & Southern |  | Allow small land purchases as eligible expenditure up to the per-project expenditure limit (provided network companies can reasonably justify such purchases as necessary early development) |  | This expenditure can be claimed as part of the relevant re-opener application. | Closed
22 | 2021-03-16 | Scottish & Southern | Maximum spend cap | Allow network companies to flex this cap if required on an exceptional and justified basis |  | Where companies are taking on more material work that goes beyond the specified cap, an application would need to be made under the relevant re-openers. | Closed
23 | 2021-03-16 | Scottish & Southern |  | The Governance Document should refer to the appropriate licence condition, in order to avoid any future confusion if e.g. Ofgem were to change the NZARD UIOLI allowance amounts. |  | The document now refers to the licence conditon. | Closed
24 | 2021-03-16 | Scottish & Southern |  | Clarification over unspent funds: assumption that these are carried over |  | We have added further clarification to the final version of the document to confirm the allowance is for the duration of the price control, and no 'per year' split applies. | Closed
25 | 2021-03-16 | Northern Powergrid |  | Unclear definition of "Low regret" in 2.3 and 2.4, potentially leading to application of subjective judgments | Replace with a clear standard of evidence that will allow licensees to be sure that they are complying with the requirement. For example, “The NZARD allowance may be used where there is a reasonable prospect that the development costs could culminate in a project that is eligible for funding under one of the reopeners provided for in the governance document”. | We have added further clarification in the text on what we mean by low regret. | Closed
26 | 2021-03-16 | Northern Powergrid |  | Common proforma in 2.6 not specific or time-bound and may not be possible to meet, as well as giving Ofgem the ability to require changes at any time | Paragraph 2.6 should, therefore, be amended such that: a) The process for developing the common proforma is re‐specified and sets out sufficient detail to enable licensees to comply with it; and b) Ofgem’s powers with respect to the timing of modifications to the common proforma are limited and specified in that process (recognising that this is without prejudice to Ofgem’s normal information gathering powers). | The common proforma is currently being developed by the relevant licensees and we will continue to work collobaratively with licensees to ensure licensees have an appropriate input into any standardized set of information we expect them to use. | Closed
27 | 2021-03-16 | Northern Gas Networks | Para 2.3 | The wording of this paragraph implies that the allowance relates only to capital projects, which is at odds with discussions that have been held with Ofgem regarding other net zero facilitation projects that may not be classed as capital expenditure. These could include, Local Area Energy Plans or progressing key changes to network and licence codes. Whilst we understand that it could also be implied that these “non-capital” projects fall under “early development work” outlined from paragraph 2.7, we suggest providing clarity in this paragraph that small net zero facilitation projects are not limited to capital projects. |  | We have made a dinstinction between what conditions apply when licensees use this fund for capital projects and where they don't. We think the early development part of the fund captures what's mentioned in this comment, and we have expanded the text to explicitely mention the Local Area Energy Plans | Closed
28 | 2021-03-16 | Northern Gas Networks |  | we consider that the approach and definition of Small Net Zero Facilitation Projects strand could be clearer and it would be beneficial for the governance document to define the likely types of work that would be accepted as being low regrets, low policy risk, with a certainty of outcomes that provide clear evidence of a need and benefit for customers. If the intention is for the governance document to be non-binding and for these discussions to be resolved through the engagement process and pipeline of projects, this should be explicitly stated for the avoidance of doubt. |  | We have added further clarification in the text on what we mean by low regret. | Closed
29 | 2021-03-16 | Northern Gas Networks | Para 2.7 | It is currently not clear, within paragraph 2.7, whether the NZARD can be used to support and develop Local Area Energy Plans (LAEPs). |  | We have included LAEPs within the text. | Closed
30 | 2021-03-16 | Southern Gas Networks | Para 2.2 | Front End Engineering Design (FFED) definition required |  | We do not consider that these needs to be a defined term in the governance document. We are open to, and plan on engaging with licensees on the detail at the appropriate point in the process. | Closed
31 | 2021-03-16 | SP Energy Networks | Review section | "NZARD Licence Condition" is not defined and should be. Noted further that the term "NZARD Licence Condition" is only used once in this guidance (and that use is within this paragraph). |  | we have now defined NZARD. | Closed
32 | 2021-03-16 | SP Energy Networks | Definitions | Under the MSIP definition Special Licence Condition 3.14 should be cross-referenced to be consistent with the treatment of other definitions. |  | We have updated the text to make reference to the SC. | Closed
33 | 2021-03-16 | SP Energy Networks | Definitions | Under the Net Zero re-opener definition Special Licence Condition 3.6 should be cross-referenced to be consistent with the treatment of other definitions. |  | We have updated the text to make reference to the SC. | Closed
34 | 2021-03-16 | SP Energy Networks | General | There should be two separate guidance documents. |  | Whilst we haven't seperated the docs - we have made it very clear what applies to ET and what doesn't, with additional text. | Closed
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53