## FBC transition timeline
2021 | [9 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Programme Milestones
M1: FBC Decision
M2: AWG recommendation delivered
M3: DB Start
M4: PMO/SI/PCC/iPA fully functioning
M5: Physical baseline delivered
M6: Code change and detailed design recommendations delivered
M7: Smart Meters Act powers enabled
M8: Code changes delivered
M9: System integration testing start
M10: Central systems ready for migrating MPANs
M11: Start of 1 year migration for UMS/Advanced
M12: Start of 1 year migration period for Smart/Non-Smart
M13: Load Shaping Service switched on
M14: All suppliers need to be able to accept MPANs under the new TOM (one way gate)
M15: Full transition complete
[56 empty] | M16: | Cut over to new settlement timetable
Switching Programme Key Phases / Milestones
REC v3 consultation |  |  |  | Ofgem directs REC v2 changes |  |  |  |  | REC v3 to Code Panels to approve |  |  | Ofgem directs REC v3 changes |  | REC v3 go-live
|  | UEPT and E2E Testing | [9 empty] | Transition Testing |  |  | Go-live
Programme Mobilisation
PM1: procurement/mobilisation of PMO/SI/PPC/iPA
PM2: Programme rebaseline
PM3: Ofgem Handover
Industry / Ofgem Work
ID1: AWG
ID2: Ofgem decision on AWG recommendations
ID3: Set-up E2E Design group
ID4: Comms technology selection scope determined
ID5: E2E Design (PMO)
ID6.a:CCDG - Transition/migration work
ID6.b: CCDG redlinning code changes
ID7: BEIS activate Smart Meter Act powers
ID8: Code and licence changes implementation
Design and build
DB1: Elexon central system design and build
| DB2a: DCC/SEC process to confirm costs and changes needed | [9 empty] | DB2b: DCC Design and Build
DB3: Registration system changes design and build
DB4: Communication network changes / development
DB5: DNO/iDNO system changes design and build
DB6:Supplier Agent - Advanced Segment design and build
DB7: Supplier Agent - Unmetered Supplies Segment design and build and data cleanse
DB8: Supplier Agent - Smart / Non Smart Segment design and build
[14 empty] | DB9:Supplier System design and build | [11 empty] | DB10: Supplier business readiness period
[18 empty] | DB11: Late mover supplier design and build | [11 empty] | DB12: Late mover supplier business readiness period
Testing
[20 empty] | TE1: Pre-Integration Testing | [8 empty] | TE2: System Integration Testing | [5 empty] | TE3: System Proving
TE4: Elexon Central System Pre-Integration Testing
TE5: Registration Systems Pre-Integration Testing
[23 empty] | TE6: DCC SIT |  |  | TE7: DCC UIT |  | TE8a: Go-live governance |  |  |  | TE8b: DCC system go live
TE9:Comms network Pre-Integration Testing
TE10: DNO/iDNO Pre-Integration Testing
TE11: SIT Participants (agents and suppliers) Pre-Integration Testing
TE12: Security Testing
TE13: Connectivity Testing
TE14: Basic Message exchange (inc. validation of error handling)
TE15: E2E Testing
TE16: Operational Testing
TE17: Non-functional testing
TE18: Security Testing
TE19: E2E Testing Sandbox
Migration / Transition
MT1: Design TOM performance assurance regime
MT2: suppliers collect customer data sharing preferences under new MHHS data sharing framework.
MT3: Smart Data Service accede to the SEC and complete DCC entry (SREPT and UEPT)
[26 empty] | MT4a: Supplier Agent Advanced Segment Pre-Qual | [8 empty] | MT4b: Supplier Agent Advanced Segment Qualification
[26 empty] | MT5a: Supplier Agent UMS Segment Pre-Qual | [8 empty] | MT5b: Supplier Agent UMS Segment Qualification
[26 empty] | MT6a: Supplier Agent Smart / Non Smart Segment Pre-Qual | [8 empty] | MT6b: Supplier Agent Smart / Non Smart Segment Qualification
[26 empty] | MT7a: Supplier Pre-Qual | [8 empty] | MT7b: Supplier Qualification
MT8: Supplier / Agent migration planning
MT9: UMS/Advanced Migration Period
MT10: Smart/Non Smart Migration Period
MT11: Populate LSS with meter data

## Milestone Descriptions
Milestone | Milestone type | Milestone | Date | Description
M1 | Level 1 | FBC Decision | 2020-04-21 | Publication of the Full Business Case, which includes the transition plan and decision on the TOM.
M2 |  | Architecture Working Group (AWG) Recommendation delivered | 2020-06-21 | The AWG will deliver recommendations providing guidance for the solution architecture required to enable the DWG’s TOM which will set the framework for subsequent IT system design.
M3 |  | DB Start | 2020-08-21 | The DB (Design and Build) phase will commence in August 2021 with Elexon's Central System, followed by DCC in Feb 2022 and other parties in May 2022.
M4 |  | PMO/PPC/SI/IPA fully functioning | 2021-10-21 | PMO/SI/PPC/IPA have stood up their team and are fully operational with all programme management processes and governance forums established.
M5 | Level 1 | Physical baseline delivered | 2020-04-22 | In order for the other parties to commence the DBT phase a complete Physical Baseline, aligning both technical and regulatory designs, will be delivered.
M6 | Level 1 | Code change and detailed design recommendations delivered | 2022-04-22 | The CCDG will deliver the recommendations aimed at addressing any outstanding areas of the DWG’s TOM design, and will deliver the recomendations for the changes to the Industry Codes and subsidiary documents necessary to enable the TOM.
M7 |  | Smart Meters Act powers enabled | 2022-05-22 | Time limited (5 year) powers in Primary Legislation for Ofgem to make changes to Industry Codes for the purposes of MHHS are activated.
M8 |  | Code changes delivered | 2022-11-22 | All changes to regulation (licences, industry codes (including BSC, SEC, REC, DCUSA)) have been made setting out the regulatory baseline.
M9 | Level 1 | System Integration Testing Start | 2020-08-23 | System Integration Testing (SIT) will commence in August 2023. This test phase involves the central parties (Elexon, DCC, comms network providers and the registration system providers) along with a small number of agents and suppliers.
M10 |  | Central systems ready for migrating MPANs | 2020-09-24 | Following completion of the testing phase (excluding TE18 Security Testing), the Central Systems (BSC central systems, registration, DCC and communication systems) will be ready to initiate migration of Meter Point Administration Numbers (MPANs) from the current market roles into the new market roles.
M11 | Level 1 | Start of 1 year migration for UMS/Advanced | 2024-10-24 | Start of migration window for suppliers to move all UMS and advanced meter points to be settled in the new arrangements.
M12 |  | Start of 1 year migration for Smart/Non-smart | 2024-11-24 | Start of migration window for suppliers to move all smart and non-smart meter points to be settled in the new arrangements.
M13 |  | Load Shaping Service switched on | 2024-11-24 | The LSS will be switched on after a period used to gather and validate settlement period level data from the smart meter data service.
M14 | Level 1 | All suppliers must be able to accept MPANs under the new TOM (one way gate) | 2020-02-25 | Deadline by which all suppliers must have the systems and services in place to accept MPANs under the new TOM. From this point MPANs cannot be moved back into NHH regime on change of supplier.
M15 | Level 1 | Full transition complete | 2020-10-25 | Completion of implementation activities including 1 year migration.
M16 | Level 1 | Cut over to new settlement timetable | 2025-11-25 | The date of the cut over to the new settlement timetable will occur after the end of migration. The decision on when the settlement timetable should be reduced should be taken nearer the time, and on market monitoring against trigger points. We think that industry should ensure that the new settlement timetable is introduced as soon as practical after the end of migration, but if this is longer than 4 months after the end of migration then this decision should be brought to Ofgem.

## Activity Descriptions
Ref. | Activity | Description | Parties Involved | Dependencies | Key Assumptions
PM1 | Procurement/mobilisation of PMO/SI/PPC/IAP | Industry party/Ofgem recruits/procures PMO/SI/PPC and IAP functions and these functions then embed and bring themselves up to speed on MHHS and the plan. | - Elexon - PMO - SI - PPC - IAP
PM2 | Programme rebaseline | PMO-led process to review programme plan and rebaseline (and take ownership of new plan). | All programme parties | PM1 | - Further detailed information is available (such as the transition and migration details from the CCDG and information regarding the architecture design) to enable a proper and evidenced based re-baseline
PM3 | Ofgem handover to central programme functions | Period of dual-running of Ofgem-led governance and new programme governance. Activity is designed to derisk transition to new programme arrangements | - Ofgem - PMO - PPC - SI | PM1
ID1 | Architecture Working Group (AWG) | Elexon-led working group producing reference architecture reccomendation for the Target Operating Model | AWG members | None | - Includes current work scope only. Does not include potential AWG follow-up activity if industry/Ofgem do not support the recommendation.
ID2 | Ofgem decision on AWG recommendation | Ofgem reviewing AWG recommendations and deciding whether to accept them as the basis for further design for the implementation of the programme | Ofgem | ID1 | - Ofgem continues to takes programme decisions during the hand over of the programme to indsutry
ID3 | Set-up E2E Design Group | Ofgem or delivery party developing Terms of Reference for the group, including constituency model and running process to appoint members/representatives | Ofgem delivery party | ID1 | - Ofgem/delivery party is able to undertake activity on a "no regrets" basis in parallel to making a decision on the AWG recommendations to enable both activities to be undertaken at the same time
ID4 | Comms technology selection scope determined | Further detail determined on the AWG recommended reference architecture to set the scope for technology selection. | - All programme parties - PMO - SI | ID2, ID3 | - Decision making rights are granted through governance structure and Ofgem involvement in decision making process is not necessary - Ofgem give a "no regrets steer" post-AWG to enable this activity to start in parallel to establishing E2E Design Group
ID5 | E2E Design | PMO chaired process to agree a physical baseline, including comms technology choices, to provide detail necessary for all parties to commence design and build of systems | All programme parties PMO | ID3, ID4 | - Decision making rights are granted through governance structure and Ofgem involvement in decision making process is not necessary - Consultation and engagement is on an ongoing basis and time for formal consultations at the end of the process (as has been the case with AWG and CCDG) is not necessary - Activity can begin before comms technology choices are made but cannot finish before that is achieved
ID6a | Code Change and Development Group (CCDG) - Transition/Migration work | Elexon-chaired working group producing detailed information on the process for transition and migration (including qualification). | CCDG members | None
ID6b | Code Change and Development Group (CCDG) - redlinning code changes | Elexon-chaired working group producing detailed code drafting for all BSC changes and consequential changes to other Codes to implement the programme | CCDG members | None
ID7 | BEIS activate Smart Meter Act powers | BEIS prepare a notice to activate the Smart Meter Act sections that will give Ofgem time-limited powers to change codes and licences to implement the programme | BEIS | None
ID8 | Code and licence changes implemented | Ofgem consult on and implement the package of changes to codes detailed by the CCDG to implement the MHHS | Ofgem | ID6b, ID7 | - Ofgem undertakes a sense check and not a detailed review of CCDG outputs - All industry codes are fully engaged in process and deliver coordinated and integrated set of code changes that accurately reflect the technical design and TOM
DB1 | Elexon central system design and build | Elexon undertake detailed design and make changes to BSC central systems in line with Target Operating Model | Elexon | ID2
DB2a | DB2a: DCC/SEC process to confirm costs and changes needed | Governance process to detail out the change and scrutinise and approve the costs to enable DCC to start their design and build of the changes. | SEC DCC SEC parties Ofgem | M1 | - Assumption is that all the required business requirements are known at the FBC. - the SEC process does not throw up any issues
DB2b | DCC Design and Build | DCC makes changes to their systems (CSS and smart metering) in line with the Target Operating Model. This is for both SMETS1 and SMETS2 meters | DCC | DB2a
DB3 | Registration system changes design and build | DNOs/iDNOs deliver changes to MPRS in line with Target Operating Model | DNOs/iDNOs and their service providers | ID5 | - Some work can start on the design following AWG recommendations, but the physical baseline from the E2E Design Group is needed for design work to progress beyond initial stages
DB4 | Communications network changes / development | Following a comms technology solution chosen they undertake the detailed design and build. Changes are also made to the DTN in line with Target Operating Model | - comms technology solution - Electralink | ID4, ID5 | - AWG outputs provide clear recommendations on requirements for communications networks - E2E Design group decides on the interface specifications for the new system and the changes required for the DTN
DB5 | DNO/iDNO system changes design and build | DNOs/iDNOs design changes to their systems (e.g. DUoS billing) to support the new Target Operating Model | - DNOs/iDNOs and their service providers | - ID5 - Code modifications network access / charging are available | - Policy decisions on network access / charging continue to be aligned with Target Operating Model (e.g. granularity of charging and design of load shaping service)
DB6 | Supplier agent - advanced segment design and build | Agents undertake detailed design work and make changes to their systems in line with the Target Operating Model | Supplier agents | ID5 | - Limited changes are necessary for existing HH agents as the design of the new TOM services are very similar
DB7 | Supplier agent - unmetered supplies segment design and build and data cleanse | Agents undertake detailed design work and make changes to their systems in line with the Target Operating Model. A data cleanse activity is needed as agents will need to consolidate multiple MPANs to a smaller number to be settled as part of the HH regime. | Supplier agents | ID5 | - Limited changes (although more than for advanced meters) as design of the new TOM services are similar to the current approach
DB8 | Supplier agent - smart / non-smart segment design and build | Agents undertake detailed design work and make changes to their systems in line with the Target Operating Model | Supplier agents | ID5 | - Significant activity involved because the entirely new nature of the service is unlike current services operated by agents
DB9 | Supplier system design and build | Suppliers undertake detailed design work and make changes to their systems in line with the Target Operating Model. Applies to suppliers who will participate in Systems Integration Testing | Suppliers / third party service providers | ID5 | - Significant activity that will involve changing range of systems - There will be a range between suppliers based on the complexity of their systems in how long this activity will take
DB10 | Supplier business readiness period | Suppliers undertaking business (not technical) preparations; such as training, updating customer engagement protocols, improving forecasting (likely using half-hourly data) and trading functions | Suppliers / third party service providers | - ID5 - DB9 | - This period is a range and there will be a range in how long suppliers take to complete these based on the complexity of their systems
DB11 | Late mover supplier system design and build | Suppliers not involved in programme testing phase undertake detailed design work and make changes to their systems in line with the Target Operating Model. | Suppliers / third party service providers | Switching Programme go-live | - Significant activity that will involve changing range of systems - There will be a range between suppliers based on the complexity of their systems in how long this activity will take
DB12 | Late mover supplier business readiness period | Suppliers not involved in programme testing phase undertaking business (not technical) preparations; such as training, updating customer engagement protocols, improving forecasting (likely using half-hourly data) and trading functions | Suppliers / third party service providers | Switching Programme go-live DB11 | - This period is a range and there will be a range in how long suppliers take to complete these based on their risk appetite and internal processes
TE1 | Pre-Integration Testing | This testing is conducted internally by each party. Testing is against integration stubs that are created by the party, or potentially against a simulator created by the SI. The aim of the testing is to prove that systems are ready to enter the SIT testing phase with other parties. Appropriate test scope and criteria will need to be defined by the SI and/or Programme Manager | - Elexon - Registration service providers - DCC - Comms network providers - DNOs/iDNOs - Agents - Suppliers - SI | n/a - Umbrella activity in plan | PIT testing is not coordinated centrally, but clear exit criteria / requirements on each party are specifiied by the SI and assured against before parties can participate in System Integration Testing
TE2 | System Integration Testing | This test phase involves the central parties (Elexon, DCC, comms network providers and the registration system providers) along with a small number of agents and suppliers. There are two aims to the testing: (1) prove basic connectivity between systems (2) prove basic message exchange and functionality between systems (including error handling for malformed messages) | - SI/PPC/PMO - Elexon - Registration Service pproviders - Comms network providers - DCC - DNOs/iDNOs - Agents (subset) - Suppliers (subset) | n/a - Umbrella activity in plan | A selection of programme parties are involved in SIT - a process to select parties for participation will be developed and implemented
TE3 | System Proving | These three test phases involves the central parties along with a small number of agents and suppliers. There are three phases: (1) E2E: prove more complex E2E scenarios (2) Operational Testing: prove operational processes (disaster, failover, SOLR etc, incident management etc.) (3) Non-Functional Testing: prove non-functional requirements of central systems (e.g. throughput, security etc.) | - SI/PPC - Elexon - Registration Service providers - Comms network providers - DCC - DNOs/iDNOs - Agents (subset) - Suppliers (subset) | n/a - Umbrella activity in plan
TE4 | Elexon central system testing | Testing of internal systems to ensure they deliver against the physical baseline. Passing this phase is a prerequisite for System Integration Testing | Elexon | DB1
TE5 | Registration system testing | Testing of internal systems to ensure they deliver against the physical baseline. Passing this phase is a prerequisite for System Integration Testing | Registration service providers | DB2 | - Registration service providers will be responsible for all testing with the exception of non-functional and operational testing (these will be the responsibility of DNOs/iDNOs). Both parties may be involved in E2E testing
TE6 | DCC SIT | Testing of internal systems and in particular integration of DSP and CSP systems | DCC | DB3a
TE7 | DCC UIT | Once DCC systems are tested internally, external parties perform a user acceptance test (User Integration Testing) to prove the DCC systems are error free and function in line with specifications | - DCC - Agents - Suppliers | - TE6 - TE11 | At least 2 MDR parties are ready to carry out UIT.
TE8a | DCC go-live governance | Formal SEC-led approvals process before DCC can declare go-live. Passing this phase is a prerequisite for System Integration Testing | - SEC - DCC | TE7
TE8b | DCC system go live | Formal SEC-led approval process before DCC can declare go live of the new system changes. This is to be included in their Nov go-live release. Once go live is complete the new user role functionality is available for use, but may not be used until the MDR systems are ready and tested and qualified. | -SEC - DCC | TE8a
TE9 | Comms network pre-integration testing | Testing of internal systems to ensure they deliver against the physical baseline. Passing this phase is a prerequisite for System Integration Testing | - comms providers | DB4
TE10 | DNO/iDNO system pre-integration testing | Testing of internal systems to ensure they deliver against the physical baseline. Passing this phase is a prerequisite for System Integration Testing | Registration service providers | DB5 | - Registration service providers will be responsible for all testing with the exception of non-functional and operational testing (these will be the responsibility of DNOs/iDNOs). Both parties may be involved in E2E testing
TE11 | SIT participants pre-integration testing | Testing of internal systems to ensure they deliver against the physical baseline. Passing this phase is a prerequisite for System Integration Testing | - Agents (subset) - Suppliers (subset) | - DB6 - DB7
TE12 | Security Testing | Independent penetration (pre-System Proving)
TE13 | Connectivity Testing | Basic testing of connections between parties | - SI/PPC - Elexon - Registration service providers - Comms network providers - DCC - DNOs/iDNOs - Agents (subset) - Suppliers (subset) | TE1 | - not all parties need to be ready for this to commence. Will need ELEXON, comms network provider and Registration service providers ready at a minimum
TE14 | Basic Message exchange (inc. validation of error handling) | Basic testing of simple messages/transactions between multiple parties, including testing error handling processes | - SI/PC - Elexon - Registration service providers - Comms network providers - DCC - DNOs/iDNOs - Agents (subset) - Suppliers (subset) | TE1
TE15 | E2E testing | Coordinated testing to prove more complex E2E scenarios. Likely to include complete runs of the settlement over both compressed and actual timelines. | - SI/PPC - Elexon - Registration service providers - Comms network providers - DCC - DNOs/iDNOs - Agents (subset) - Suppliers (subset) | TE2 | - Settlement runs are technically the same process which gets repeated at different intervals with additional data submitted/revised - Five month window allows for multiple R1 settlements (occurs at c.T+33WD), to reduce commercial risk (or perception of risk)
TE16 | Operational Testing | Coordinated testing to prove operational processes (disaster, failover, SOLR etc, incident management etc.) | - SI/PPC - Elexon - Resgistration service providers - Comms network providers - DCC - DNOs/iDNOs - Agents (subset) - Suppliers (subset) | - TE2 - TE15 | Operational testing cannot start before E2E testing has proved certain functionality but can commence before that activity finishes
TE17 | Non-functional testing | Coordinated testing of non-functional requirements (e.g. capacity, backup, recovery etc.) | - SI/PPC - Elexon - Registration service providers - Comms network providers - DCC - DNOs/iDNOs - Agents (subset) - Suppliers (subset) | TE2
TE18 | Security Testing | Independent penetration (post-System Proving) |  | TE3
TE19 | E2E Testing Sandbox | During this period participants who have completed qulification testing can enter an E2E sandbox in which the central systems will be operating as live. This will allow participants to conduct any further testing beyond qualification that they wish to undertake. | - SI/PPC - Elexon - Registration service providers - Comms network providers - DCC - DNOs/iDNOs - Agents - Suppliers | TE3 | SI will run an approval process to grant access to the E2E Testing Sandbox. Support including error handling will be available from central parties
MT1 | Design TOM Performance Assurance Regime | Elexon-led process to define Performance Assurance regime for the TOM (including the migration period) | Elexon | ID2
MT2 | Suppliers collect customer data sharing preferences under new MHHS data sharing framework. | Suppliers update data access policies and processes and put in place new systems to agree customer preferences. The long activity reflects the need for suppliers to update the customer data consents, including on contract renewal. | Suppliers
MT3 | Smart data service accedes to SEC and completes DCC entry | Agents not already DCC users to complete SEC accession (and security) processes, obtain DCC connection and adapter services and complete DCC entry testing | - Agents - SEC - DCC | ID9 | - Agents are able to start SEC accession process before any HHS-related changes are made to DCC systems - Agents are able to start SEC accession processes in Other User category and this will not be affected by HHS code changes (ie. no dependency) - No capacity constraints in SEC security assessment process (unlike smart meter rollout)
MT4a | Supplier agent advanced segment pre-qualification | Preparatory activity by agents to prepare for qualification processes. This will include undertaking connectivity testing so that they can be ready to start qualification testing. | Agents | DB6 | Some parties will have incentives to commence early preparations in order to be be ready to begin qualification at the earliest opportunity - this is BSC qualification, and not other code qualification
MT4b | Supplier agent advanced segment qualification | Agents qualify in new services as per the Target Operating Model. This will include structured qualification testing. Tranching may be used to manage the number of parties undertaking testing at any one time. | - Agents - Elexon | TE15 | No capacity constraints from Elexon (or BSC auditors) affect qualification processes - this is BSC qualification, and not other code qualification - the start of TE15 is a dependancy, but full qualification can begin as this progresses. - qualification length is 8 months, and this is on the assumption the requirements for the Advanced segment is less onerous and reflects more of a 'requalification' process.
MT5a | Supplier agent UMS segment pre-qualification | Preparatory activity by agents to prepare for qualification processes. This will include undertaking connectivity testing so that they can be ready to start qualification testing. | Agents | DB7 | Some parties will have incentives to commence early preparations in order to be be ready to begin qualification at the earliest opportunity - this is BSC qualification, and not other code qualification
MT5b | Supplier agent UMS segment qualification | Agents qualify in new services as per the Target Operating Model. This will include structured qualification testing. Tranching may be used to manage the number of parties undertaking testing at any one time. | - Agents - Elexon | TE15 | No capacity constraints from Elexon (or BSC auditors) affect qualification processes - this is BSC qualification, and not other code qualification - the start of TE15 is a dependancy, but full qualification can begin as this progresses. - qualification length is 8 months, and this is on the assumption the requirements for the UMS segment is less onerous and reflects more of a 'requalification' process.
MT6a | Supplier agent smart/non-smart segment pre-qualification | Preparatory activity by agents to prepare for qualification processes. This will include undertaking connectivity testing so that they can be ready to start qualification testing. | Agents | DB8 | Some parties will have incentives to commence early preparations in order to be be ready to begin qualification at the earliest opportunity - this is BSC qualification, and not other code qualification
MT6b | Supplier agent smart/non-smart segment qualification | Agents qualify in new services as per the Target Operating Model. This will include structured qualification testing. Tranching may be used to manage the number of parties undertaking testing at any one time. | - Agents - Elexon | TE15 | No capacity constraints from Elexon (or BSC auditors) affect qualification processes - this is BSC qualification, and not other code qualification - the start of TE15 is a dependancy, but full qualification can begin as this progresses. - qualification length is 12 months, as it is thought the process is more onerous then UMS/advanced.
MT7a | Supplier pre-qualification | Preparatory activity by suppliers to prepare for qualification processes. This will include undertaking connectivity testing so that they can be ready to start qualification testing. | Suppliers | DB9 | Some parties will have incentives to commence early preparations in order to be be ready to begin qualification at the earliest opportunity - this is BSC qualification, and not other code qualification
MT7b | Supplier qualification | Suppliers qualify in new services as per the Target Operating Model. This will include structured qualification testing. Tranching may be used to manage the number of parties undertaking testing at any one time. | - Suppliers - Elexon | TE15 | No capacity constraints from Elexon (or BSC auditors) affect qualification processes - this is BSC qualification, and not other code qualification the start of TE15 is a dependancy, but full qualification can begin as this progresses. - qualification length is 12 months, as it is thought the process would include suppliers qualifying for all three market roles.
MT8 | Supplier / Agent migration planning | Suppliers and agents discussing, preparing and making contractual arrangements for the migration process | - Agents - Suppliers
MT9 | UMS/Advanced Migration period | UMS and advanced Individual meter points are migrated to the new settlement arrangements | - SI/PPC - Elexon - Registration service providers - Comms network providers - DNOs/iDNOs - Agents - Suppliers | - MT4 - MT5
MT10 | Smart/Non smart Migration Period | Smart and non-smart individual meter points are migrated to the new settlement arrangements | - SI/PPC - Elexon - Registration service providers - Comms network providers - DNOs/iDNOs - DCC - Agents - Suppliers | MT6
MT11 | Populate Load Shaping Service with meter data | Settlement period data submitted to Elexon central systems is used to populate Load Shaping Service | Elexon | TE8b | Load shaping service needs at least 3 months of data before it can be switched on