## NGGD_ext
Question No. | Proforma section | NIC Criteria | Topic | Question | Date question asked | Date response required | Date received | Follow up to Question #
1 | NA | e) Partners and ext. funding | External funding | Is the £6.5m of funding from Advanced Plasma Power linked to success in the DfT bid or success in the NIC bid? | 2015-08-20 | 2015-08-24 | 2015-08-24
2 | NA | e) Partners and ext. funding | External funding | Are there any governance arrangements that are tied to the DfT funding? If so, please can you provide further information? | 2015-08-20 | 2015-08-24 | 2015-08-24
3 | 5.1 | c) Generates new knowledge | Knowledge Dissemination | Are there any links with your dissemination plan for this project and the work that would have been completed under the Pilot Plant Project? | 2015-08-20 | 2015-08-24 | 2015-08-24
4 | 3.1 | a) Enviro+consumer bens | Benefit Modelling | Why are the project partners expecting full scale BioSNG plants to be fundable without support by 2025 and not before? | 2015-08-25 | 2015-08-27 | 2015-08-27
5 | 3.1 | e) Partners and ext. funding | External funding | Have the project partners got a gauge on the confidence of private investors for this type of long term investment even after this small scale commercial plant is completed? How will that confidence be assured? By validating the current cost model (currently predict a loss)? | 2015-08-25 | 2015-08-27 | 2015-08-27
6 | 3.1 | a) Enviro+consumer bens | Benefit Modelling | The business case states that a 658GWh (full scale) facility can achieve a return if gas price is £18MWh and a smaller facility requires a gas price of £26/MWh. How are the project partners justifying the savings due to a larger scale facility? | 2015-08-25 | 2015-08-27 | 2015-08-27
7 | 3.2 | a) Enviro+consumer bens | Benefit Modelling | What happens to the roll out plant if the price for natural gas remains as low as it is currently. | 2015-08-25 | 2015-08-27 | 2015-08-27
8 | General | e) Partners and ext. funding | Research Basis | What have the results of the pilot plant shown in terms of technical viability of the overall process, conversion efficiencies, waste product management and parasitic loads? How do the results match the predictions in the previous studies? | 2015-08-25 | 2015-08-27 | 2015-08-27
9 | General | d) Is innovative | Proof of Innovation | The GDNs have an output commitment to introduce voluntary distributed gas entry standards, but they were not funded as part of totex for the connection, this would be funded by the customer wanting to be connected. Why is this any different to any other customer wanting a distributed gas entry connection? | 2015-08-25 | 2015-08-27 | 2015-08-27 | 24
10 | General | e) Partners and ext. funding | Benefit Modelling | The submission considers the benefit for the GDNs for lower NTS exit capacity charges. With the potential for BioSNG to meet 40% of UK domestic gas demand have NGGD considered the wider impact/benefit for the NTS eg future reduced load related expenditure? | 2015-08-25 | 2015-08-27 | 2015-08-27 | 25 & 26
11 | General | a) Enviro+consumer bens | Benefit Modelling | What is the ongoing cost liability for NGG for operating the connection? Will there be any future revenue streams (charging) for NGG? | 2015-08-25 | 2015-08-27 | 2015-08-27
12 | 2.1.2 (p7) | d) Is innovative | Background | You reference an NNFCC report in footnote 7. Please can you provide a copy? | 2015-08-28 | 2015-09-03 | 2015-09-03
13 | 3.1 | c) Generates new knowledge | Benefit Modelling | How do the potential benefits claimed for this project compare to the potential benefits claimed for the Pilot project? | 2015-08-28 | 2015-09-03 | 2015-09-03
14 | 4e | c) Generates new knowledge | Knowledge Dissemination | Does any learning related to the DfT's funded part of the project have any potential impacts on any IPRs arising from the NIC funded part of the project? | 2015-08-28 | 2015-09-03 | 2015-09-03
15 | Appendix 8 | a) Enviro+consumer bens | Project Plan | Can NGGD supply detailed cash-flows timings of the investments, running costs and revenues underlying Appendix 8? | 2015-08-28 | 2015-09-03 | 2015-09-03
16 | 4a | a) Enviro+consumer bens | Benefit Modelling | The environmental benefits case appears to be based on BioSNG vs. fossil fuels. To produce substantive amounts of BioSNG will require a significant amount of RDF. Has the project considered: (i) the opportunity cost of using RDF for BioSNG as opposed to other uses? (ii) how much of the potentially available RDF would be needed to produce the amount of BioSNG needed to deliver the benefits quoted between 2020-2050? | 2015-08-28 | 2015-09-03 | 2015-09-03
17 | 4a | a) Enviro+consumer bens | Benefit Modelling | Why has NGGD decided that BEAT 2 is an appropriate methodology to use in the project objectives? | 2015-08-28 | 2015-09-03 | 2015-09-03
18 | 4a | a) Enviro+consumer bens | Benefit Modelling | Can NGGD provide information on the EC RED methodology referred to? Do you have any information to provide a greater insight into the basis of these measurements and whether they account for other uses of RDF/other waste to energy systems | 2015-08-28 | 2015-09-03 | 2015-09-03
19 | 4b(i) | a) Enviro+consumer bens | Project Logistics | NGGD suggest (page 22) that commercial support is unavailable unless there is a commercial plant operating continuously at a significant scale. Why can't continuous operation not be demonstrated with the pilot plant? | 2015-08-28 | 2015-09-03 | 2015-09-03
20 | 4 | a) Enviro+consumer bens | Benefit Modelling | On what basis has the scale of the plant been selected? What evidence is there that this is adequate for potential commercial scale interests. | 2015-08-28 | 2015-09-03 | 2015-09-03
21 | Appendix 5 | g) Robust methodology/ready to implement | Project Plan | Please can you clarify the stage gates in your project plan? It would also be helpful to understand the expected spending by each stage gate. | 2015-09-08 | 2015-09-11 | 2015-09-11
22 | General | c) Generates new knowledge | Proof of Innovation | Please can you clarity: i. What questions are unanswered by the Pilot BioSNG project? ii. What questions are unanswered by the DfT funding? iii. Subject to (i) and (ii), what questions will be answered by the additional NIC funding? | 2015-09-08 | 2015-09-11 | 2015-09-11
23 | General | g) Robust methodology/ready to implement | Consumer engagement | Please can you clarify your plans for engaging the local community if the project goes ahead? | 2015-09-08 | 2015-09-11 | 2015-09-11
24 | General | d) Is innovative | Connections learning | Following up on Q&A9, we note your response that BioSNG is not identical to biomethane, and there may be new connection issues (eg gas quality and clean up) that will be explored as part of this project. (i) Is your assumption that, if successful, the learning from making this new type of gas connection will remove any existing barriers to making similar connections in the future for GDNs? (ii) Can you clarify what the learning will be for you (and all GDNs) around the grid connection that the NIC would fund. | 2015-09-15 | 2015-09-17 | 2015-09-17
25 | General | e) Partners and ext. funding | Benefit Modelling | Following up on Q&A 10, has any stakeholder engagement been carried out with the NTS to understand what wider costs/benefits might be even if they have not been quantified? | 2015-09-15 | 2015-09-17 | 2015-09-17
26 | General | e) Partners and ext. funding | Benefit Modelling | Following up on Q&A 10. If rolled out, what are your assumptions in the central benefits case about where BioSNG will connect in terms of NTS vs GDN network? | 2015-09-15 | 2015-09-17 | 2015-09-17
27 | SDRC 9.5 | g) Robust methodology/ready to implement | SDRCs | For SDRC 9.5, please can you explain what the 'customer feedback' evidence will be? What customers will it be? | 2015-09-15 | 2015-09-17 | 2015-09-17
28 | n/a | a) Enviro+consumer bens | Benefit Modelling | Please can you clarify: • the benefits case for end consumers • the wider consumer benefits for the grid as a whole | 2015-09-29 | 2015-10-02 | 2015-10-02
29 | n/a | g) Robust methodology/ready to implement | SDRCs | Please can you clarify that the 3rd stage gate in September 2016 is linked to the ‘success’ of the primary testing phase of the Pilot Plant? This includes considering whether SDRC 9.2 should make this explicit. | 2015-09-29 | 2015-10-02 | 2015-10-02