## Actions
ID | Title | Topic/Category | Action | Action Owner | Date Raised | Due Date | Comments/Progress/Conclusion | Action Status | Closed Date
A01 | Gemserv/Electralink Attendance | Attendance | To speak to Gemserv and Electralink to see if they would be willing to attend a working group session to discuss data flows, and data they may hold. | James Crump | 2019-02-28 | 2019-03-08 | Electralink representitive invited to April session - still waiting on Gemserv. | Open
A02 | Required Switch Length | Standard A (Delayed Switches) | Ofgem to provide certainty on intention of what the required length of the switch is classed as. Is it 21 days or 35 days? | Ofgem | 2019-03-11 | 2019-03-25 | Ofgem currently working on their policy position and will feedback to the group as soon as possible. | In Review
A03 | Data Working Group Analysis | Data | To question the data working group and see if the GSOP working group woud be able to use any fo their data and/or analysis which they have available | James Crump | 2019-03-11 | 2019-03-25 | Analysis from early Switching Programme data work is available on Ofgem's website. | In Review
A04 | Compensation Guidance | Ofgem Work | Ofgem to provide a guidance document explaining the implementation of the Phase 1 of the Switching Compensation work. | Ofgem | 2019-02-28 | 2019-03-18 | JC currently speaking to Ofgem data team about the reporting of data as we need to know this in detail in order for guidance to be provided on Phase 1. Guidance will be issued as soon as possible. Hoepfully by w/c 18th March. | In Review
A05 | PCW Representitives at Group | Attendance | Group members to consider if they are able to identify suitable representatives from Price Comparison Websites who might wish to attend the group. | Group Members | 2019-03-11 | 2019-03-25 |  | Open
A07 | Data Working Group Analysis | Industry Work | Ofgem to review analysis of data issues and assess applicability to this working group. | Ofgem | 2019-03-11 | 2019-03-25 |  | Open
A08 | Retail Energy Location | Data | Ofgem to consult with colleagues in the Switching Programme to identify whether the Retail Energy Location database can be brought forward. | Ofgem | 2019-03-11 | 2019-03-25 | The REL is unlikely to be brought forward, and it is unlikely we will have a REL product in the near future as well. The timeline of procurement of the REL is being driven by the Design, Build and Test Phase of the Switching Programme which means it is now difficult to reboot the timeline for the REL now. | In Review
A09 | Responsibility for delays | Industry Work | Group members to look at the causes of delays, to identify errors and omissions in the reasons given and to identify which party was responsible for the delay in each case. | Group Members | 2019-03-11 | 2019-03-25 |  | Open
A11 | Code Body Engagement | Industry Engagement | Ofgem to lead the group in developing an action plan with relevant code bodies with regard to the timing of final bills. | Ofgem | 2019-03-11 | 2019-03-25 | Ofgem have spoken to some code bodies, such as MRA, and work has begun on the action plan for what the group's proposals are. | Open
A12 | Evidencing mechanism | Industry Work | Group members to consider questions on creating a mechanism for evidencing detriment and to make suggestions to Ofgem. | Group Members | 2019-03-11 | 2019-03-25 |  | Open
A13 | ECOES/DES Meeting Discussion | Attendance | Bring a suitable representative to a meeting that can speak on behalf of ECOES and/or DES to discuss how oftem suppliers can submit data to the GTs and DNOs to submit to ECOES/DES and to understand what issues arrise from this, including who is responsible and if they are always receptive of receiving data from suppliers. | Ofgem | 2019-03-25 | 2019-04-08 |  | Open
A14 | Data Process Risks | Industry Work | Group members to share with Ofgem any information about, or risk and concerns with, supplier’s systems regarding data processes. | Group Members | 2019-03-25 | 2019-04-08 |  | Open
Open
Switching Compensation Guaranteed Standards of Performance - Actions and Decisions
Last Updated: 28/03/2019 Next Meeting: 08/04/2019
Switching Compensation Guaranteed Standards of Performance - Actions and Decisions
Last Updated: 28/03/2019 Next Meeting: 11/04/2019

## Decisions
ID | Title | Topic/Category | Decision | Decision Owner | Decision Date | Outcome | Comments | Decision Status
D01 | ToR | Group Governance | The working group to agree on the group's terms of reference | Ofgem | 2019-02-28 | Decision Agreed | When asked there was no clear objections to the Terms of Reference. This decision can always be re-looked at at a later date, and any changes to the ToR that are required can be discussed and acted upon | Decision Made
D02 | Meeting frequency | Group Governance | The group to agree how often they would like the meetings to occur. Longer, less frequent meetings? Shorter, more frequent meetings? Or otherwise? | Whole Group | 2019-03-11 | Decision Agreed | The group agreed that the current schedule of longer meetings roughly every two weeks should be sufficient. This can be changed at a later date if required. | Decision Made
D03 | Meeting Locations | Group Governance | To take the group sessions outside of London to other locations around the country | Ofgem |  | On Hold | Ofgem are happy to look at arranging the working group meetings in different locations in order to make it easier for group participants who are based in other areas of the country to attend. However, currently due to Ofgem financial restrictions we are unable to do so in this financial year. As soon as budget restrictions are lifted, Ofgem will look into arranging future meetings outside of London. | On Hold
Switching Compensation Guaranteed Standards of Performance - Actions and Decisions
Last Updated: 28/03/2019 Next Meeting: 11/04/2019

## Meeting Dates and Attendance
Meeting Date | Attendees | Organisation | Minutes to be Issued By
2019-01-11 | James Crump (Chair) | Ofgem | 2019-01-19
| James Hardy | Ofgem
| Rachel Clark | Ofgem
| Mark Anderson | SSE
| Martyn Edwards | SSE
| Samuel Arnold | Green Network Energy
| James Evans | Hudson Energy
| Paul Fuller | ESB Energy
| Duncan Carter | COOP
| Lee Wilks | COOP
| Adam Rolph | First Utility
| Imogen Marriott | First Utility
| Helen Rafferty | EON
| Sam Woodhouse | EON
| Steve Brennan | EON
| Gregory Mackenzie | Centrica
| Sarah-Jane Russell | Centrica
| Roxanne Inskip-Kaye | Social Energy
| Andy Baugh | Npower
| Gavin Anderson | EDF
(No Webex roll call taken)
Meeting Date | Attendees | Organisation | Minutes to be Issued By
2019-01-24 | James Crump (Chair) | Ofgem | 2019-02-01
| James Hardy | Ofgem
| Iona Penman | Energy UK
| Colin Brooks | Energy UK
| Gregory Mackenzie | Centrica
| Sarah-Jane Russell | Centrica
| Joe Clark-McGhee | Octopus
| Adam Rolph | First Utility
| Imogen Marriott | First Utility
| Andrew Wooding | Utility Warehouse
(No Webex roll call taken)
Meeting Date | Attendees | Organisation | Minutes to be Issued By
2019-02-28 | James Crump (Chair) | Ofgem | 2019-03-07
| James Hardy | Ofgem
| Iona Penman | Energy UK
| Alexandra Meagher | Bulb
| Miles Rosenblatt | Bulb
(No Webex roll call taken)
Meeting Date | Attendees | Organisation | Minutes to be Issued By
2019-03-11 | James Crump (Chair) | Ofgem | 2019-03-15
| James Hardy | Ofgem
| Iona Penman | Energy UK
| Miles Rosenblatt | Bulb
| Adam Rolph | First Utility
| Andrew Wooding | Utility Warehouse
| Andy Baugh | Npower
| Gregory Mackenzie | Centrica
| Sarah-Jane Russell | Centrica
| Imogen Marriott | First Utility
| James Evans | Just Energy
| Jane Holdaway | EDF Energy
| Joe Clark-McGhee | Octopus
| Katy Ellis | EDF Energy
| Kudan Singh | Npower
| Martyn Edwards | SSE
| Sam Pearson | OVO Energy
| Sam Woodhouse | EON
| Samuel Arnold | Green Network Energy
| Chris Welby | Bristol Energy
| Craig Smith | SSE
| Gary Wallace | SSE
| Connor Adams | Scottish Power
(Webex roll-call included)
Meeting Date | Attendees | Organisation | Minutes to be Issued By
2019-03-25 | James Crump (Chair) | Ofgem | 2019-03-29
| James Hardy | Ofgem
| Iona Penman | Energy UK
| Miles Rosenblatt | Bulb
| Katy Ellis | EDF Energy
| Martyn Edwards | SSE
| Sarah-Jane Russell | British Gas
| Connor Adams | Scottish Power
| Alison Price | Npower
| Andrew Wooding | Utility Warehouse
| Jane Holdaway | EDF Energy
| Laura Richer | Just Energy
| Sam Woodhouse | EON
| Gregory Mackenzie | British Gas
Webex attendance Only