## Cover
This workbook summarises Atkins' assessment of GDNs' IT and Telecoms projects that GDNs submitted for RIIO-GD2.
GD Distribution Summary
|  | DD |  |  |  | FD
| Original funding request | Granted | Ex-ante funding reduction | Uncertainty Mechanism | Revised funding request | Granted | Ex-Ante funding Reduction | UM
Cadent | 102.867 | 7.371 | 25% | 93.039 | 102.868 | 87.7246 | 14.72% | 0
NGN | 40.0821 | 30.075 | 25% | 0 | 40.0596 | 37.3441 | 6.779% | 0
SGN | 62.7556 | 25.37 | 3.838% | 36.3731 | 62.7556 | 57.5852 | 8.239% | 0
WWU | 31.595 | 5.065 | 0% | 26.535 | 39.544 | 33.4814 | 12.65% | 1.2145

## Cadent
| Draft Determination | [6 empty] | Final Determination
New RAG Calc
Project | Justification | Definition | Resource | Cost Assurity | Requested | Granted | UM |  |  |  |  | FD Request |  | Ex-ante funding | UM | Def wtg | Res Wtg | Cost Wtg
INVP 5402 | Green | Amber | Amber | Amber | 9.828 | 7.371 |  | Green | Green | Amber | Amber | 9.828 | ◄ | 8.3538 |  | 40% | 22.5% | 22.5%
INVP 5101 | Amber | Red | Red | Red | 4.725 |  | UM | Green | Green | Amber | Amber | 4.725 | ◄ | 4.0162 |  | 40% | 22.5% | 22.5%
INVP 5103 | Amber | Amber | Red | Amber | 6.634 |  | UM | Amber | Green | Amber | Amber | 6.634 | ◄ | 5.6389 |  | 40% | 22.5% | 22.5%
INVP 5101 | Amber | Red | Red | Amber | 5.67 |  | UM | Green | Green | Amber | Amber | 5.67 | ◄ | 4.8195 |  | 40% | 22.5% | 22.5%
INVP 5104 | Green | Red | Red | Red | 2.835 |  | UM | Amber | Amber | Amber | Amber | 2.835 | ◄ | 2.1262 |  | 30% | 22.5% | 22.5%
INVP 5203 | Amber | Red | Red | Red | 0 |  | UM | Green | Green | Green | Green | 0 | ◄ | 0
INVP 5208 | Amber | Red | Red | Red | 2.117 |  | UM | Green | Green | Amber | Amber | 2.117 | ◄ | 1.7994 |  | 40% | 22.5% | 22.5%
INVP 5206 | Amber | Red | Red | Red | 1.134 |  | UM | Green | Green | Amber | Amber | 1.134 | ◄ | 0.9639 |  | 40% | 22.5% | 22.5%
INVP 5207 | Amber | Red | Red | Red | 0.756 |  | UM | Green | Green | Green | Green | 0.756 | ◄ | 0.756
INVP 5205 | Amber | Red | Red | Red | 0 |  | UM | Green | Green | Green | Green | 0 | ◄ | 0
INVP 5201 | Amber | Red | Red | Red | 3.175 |  | UM | Green | Green | Amber | Amber | 3.175 | ◄ | 2.6987 |  | 40% | 22.5% | 22.5%
INVP 5205 | Green | Red | Red | Red | 1.058 |  | UM | Green | Green | Amber | Amber | 1.058 | ◄ | 0.8993 |  | 40% | 22.5% | 22.5%
INVP 5301 | Amber | Red | Red | Red | 0.964 |  | UM | Green | Green | Green | Green | 0.964 | ◄ | 0.964
INVP 5303 | Amber | Red | Red | Red | 0.473 |  | UM | Green | Green | Green | Green | 0.473 | ◄ | 0.473
INVP 5301 | Amber | Red | Red | Amber | 3.289 |  | UM | Amber | Amber | Amber | Amber | 3.289 | ◄ | 2.4668 |  | 30% | 22.5% | 22.5%
INVP 5304 | Amber | Red | Red | Amber | 2.986 |  | UM | Amber | Green | Amber | Amber | 2.986 | ◄ | 2.5381 |  | 40% | 22.5% | 22.5%
INVP 5403 | Amber | Amber | Red | Amber | 6.615 |  | UM | Amber | Green | Amber | Amber | 6.615 | ◄ | 5.6227 |  | 40% | 22.5% | 22.5%
INVP 5404 | Green | Amber | Red | Amber | 3.969 |  | UM | Green | Green | Amber | Amber | 3.969 | ◄ | 3.3736 |  | 40% | 22.5% | 22.5%
INVP 5406 | Amber | Red | Red | Red | 2.481 |  | UM | Green | Green | Green | Green | 2.481 | ◄ | 2.481 |  | 40% | 22.5% | 30%
INVP 5407 | Amber | Red | Red | Red | 3.78 |  | UM | Amber | Green | Amber | Amber | 3.78 | ◄ | 3.213 |  | 40% | 22.5% | 22.5%
INVP 5408 | Amber | Red | Red | Red | 3.213 |  | UM | Green | Green | Amber | Amber | 3.213 | ◄ | 2.7311 |  | 40% | 22.5% | 22.5%
INVP 5409 | Green | Amber | Red | Amber | 16.16 |  | UM | Green | Green | Amber | Amber | 16.16 | ◄ | 13.736 |  | 40% | 22.5% | 22.5%
INVP 5405 | Green | Amber | Red | Red | 0 |  | UM | Green | Green | Green | Green | 0 | ◄ | 0
INVP 5501 | Amber | Red | Red | Red | 2.646 |  | UM | Amber | Green | Amber | Amber | 2.646 | ◄ | 2.2491 |  | 40% | 22.5% | 22.5%
INVP 5502 | Amber | Red | Red | Red | 0 |  | UM | Green | Green | Green | Green | 0 | ◄ | 0
INVP 5503 | Amber | Amber | Red | Amber | 9.45 |  | UM | Green | Green | Amber | Amber | 9.45 | ◄ | 8.0325 |  | 40% | 22.5% | 22.5%
INVP 5504 | Green | Amber | Red | Red | 0 |  | UM | Green | Green | Green | Green | 0 | ◄ | 0
INVP 5701 | Amber | Red | Red | Red | 0.756 |  | UM | Green | Green | Green | Green | 0.756 | ◄ | 0.756
INVP 5702 | Amber | Red | Red | Red | 0 |  | UM | Green | Green | Green | Green | 0 | ◄ | 0
INVP 5703 | Amber | Red | Red | Red | 0 |  | UM | Green | Green | Green | Green | 0 | ◄ | 0
INVP 5705 | Amber | Red | Red | Red | 0.565 |  | UM | Green | Green | Green | Green | 0.565 | ◄ | 0.565
INVP 5704 | Green | Amber | Red | Amber | 6.143 |  | UM | Green | Green | Amber | Amber | 6.143 | ◄ | 5.2215 |  | 40% | 22.5% | 22.5%
INVP D1 | Green | Red | Red | Red | 1.446 |  | UM | Amber | Green | Amber | Amber | 1.446 | ◄ | 1.2291 |  | 40% | 22.5% | 22.5%
INVP D2 | Green | Red | Red | Red | 0 |  | UM | Green | Green | Green | Green | 0 | ◄ | 0
INVP D3 | Green | Red | Red | Red | 0 |  | UM | Green | Green | Green | Green | 0 | ◄ | 0

## NGN
| Draft Determination | [6 empty] | Final Determination
New RAG Calc
Project | Justification | Definition | Resource | Cost Assurity | Original Request | Ex-ante Funding | UM |  |  |  |  | FD Request |  | Ex-ante funding | UM | Def wtg | Res Wtg | Cost Wtg
NGN INVP1 | Green | Amber | Amber | Amber | 2.3428 | 1.7573 |  | Green | Green | Green | Amber | 2.3287 | ▼ | 2.154 |  | 40% | 30% | 22.5%
NGN INVP2 | Green | Amber | Amber | Amber | 0.40266 | 0.30204 |  | Green | Green | Green | Green | 0.39321 | ▼ | 0.39321 |  | 40% | 30% | 22.5%
NGN INVP3 | Green | Amber | Amber | Amber | 1.6399 | 1.2301 |  | Green | Green | Green | Amber | 1.6235 | ▼ | 1.5017 |  | 40% | 30% | 22.5%
NGN INVP4 | Green | Amber | Amber | Amber | 2.4465 | 1.8351 |  | Green | Green | Green | Amber | 2.5977 | ▲ | 2.4029 |  | 40% | 30% | 22.5%
NGN INVP5 | Green | Amber | Amber | Amber | 0.85413 | 0.64069 |  | Green | Green | Green | Green | 0.83111 | ▼ | 0.83111 |  | 40% | 30% | 22.5%
NGN INVP6 | Green | Amber | Amber | Amber | 0.97615 | 0.73222 |  | Green | Green | Green | Green | 0.99448 | ▲ | 0.99448 |  | 40% | 30% | 22.5%
NGN INVP7 | Green | Amber | Amber | Amber | 2.1963 | 1.6475 |  | Green | Green | Green | Amber | 2.4323 | ▲ | 2.2499 |  | 40% | 30% | 22.5%
NGN INVP8 | Green | Amber | Amber | Amber | 0.54909 | 0.41206 |  | Green | Green | Green | Green | 0.56666 | ▲ | 0.56666 |  | 40% | 30% | 22.5%
NGN INVP9 | Green | Amber | Amber | Amber | 1.5862 | 1.1904 |  | Green | Green | Green | Amber | 1.6028 | ▲ | 1.4826 |  | 40% | 30% | 22.5%
NGN INVP10 | Green | Amber | Amber | Amber | 2.1963 | 1.6482 |  | Green | Green | Green | Amber | 2.2298 | ▲ | 2.0626 |  | 40% | 30% | 22.5%
NGN INVP11 | Green | Amber | Amber | Amber | 1.8303 | 1.3735 |  | Green | Green | Green | Amber | 1.9919 | ▲ | 1.8425 |  | 40% | 30% | 22.5%
NGN INVP12 | Green | Amber | Amber | Amber | 2.4404 | 1.8314 |  | Green | Green | Green | Amber | 2.428 | ▼ | 2.2459 |  | 40% | 30% | 22.5%
NGN INVP13 | Green | Amber | Amber | Amber | 2.3184 | 1.7398 |  | Green | Green | Green | Amber | 2.4199 | ▲ | 2.2384 |  | 40% | 30% | 22.5%
NGN INVP14 | Green | Amber | Amber | Amber | 3.6606 | 2.7471 |  | Green | Green | Green | Amber | 3.8131 | ▲ | 3.5271 |  | 40% | 30% | 22.5%
NGN INVP15 | Green | Amber | Amber | Amber | 1.2202 | 0.915 |  | Green | Green | Green | Amber | 1.2167 | ▼ | 1.1255 |  | 40% | 30% | 22.5%
NGN INVP16 | Green | Amber | Amber | Amber | 2.4404 | 1.83 |  | Green | Green | Green | Amber | 2.4372 | ▼ | 2.2544 |  | 40% | 30% | 22.5%
NGN INVP17 | Amber | Amber | Amber | Amber | 2.6234 | 1.969 |  | Amber | Green | Green | Amber | 2.6669 | ▲ | 2.4669 |  | 40% | 30% | 22.5%
NGN INVP18 | Amber | Amber | Amber | Amber | 3.6606 | 2.7475 |  | Amber | Green | Green | Amber | 3.515 | ▼ | 3.2513 |  | 40% | 30% | 22.5%
NGN INVP19 | Amber | Amber | Amber | Amber | 0.73212 | 0.5495 |  | Green | Green | Green | Green | 0.74308 | ▲ | 0.74308 |  | 40% | 30% | 22.5%
NGN INVP20 | Amber | Amber | Amber | Amber | 0.30505 | 0.22896 |  | Green | Green | Green | Green | 0.32397 | ▲ | 0.32397 |  | 40% | 30% | 22.5%
NGN INVP21 | Amber | Amber | Amber | Amber | 2.1353 | 1.6027 |  | Amber | Green | Green | Amber | 1.5711 | ▼ | 1.4532 |  | 40% | 30% | 22.5%
NGN INVP22 | Amber | Amber | Amber | Amber | 1.5252 | 1.1448 |  | Amber | Green | Green | Amber | 1.3327 | ▼ | 1.2328 |  | 40% | 30% | 22.5%

## SGN
| Draft Determination | [6 empty] | Final Determination
New RAG Calc
Project | Justification | Definition | Resource | Cost Assurity | Requested | Granted | UM |  |  |  |  | FD Request |  | Ex-ante funding | UM | Def wtg | Res Wtg | Cost Wtg
SGN INVP1 | Green | Green | Green | Green | 1.832 | 1.832 |  | Green | Green | Green | Green | 1.832 | ◄ | 1.832
SGN INVP2 | Amber | Red | Red | Red | 2 | 0 | UM | Green | Green | Green | Amber | 2 | ◄ | 1.85 |  | 40% | 30% | 22.5%
SGN INVP3 | Amber | Amber | Red | Red | 8 | 0 | UM | Green | Green | Green | Amber | 8 | ◄ | 7.4 |  | 40% | 30% | 22.5%
SGN INVP4 | Amber | Amber | Red | Red | 0.693 | 0 | UM | Green | Green | Green | Green | 0.693 | ◄ | 0.693 |  | 40% | 30% | 30%
SGN INVP5 | Amber | Amber | Red | Red | 0.7875 | 0 | UM | Green | Green | Green | Green | 0.7875 | ◄ | 0.7875 |  | 40% | 30% | 30%
SGN INVP6 | Red | Red | Red | Red | 2 | 0 |  | Green | Green | Green | Green | 2 | ◄ | 2 |  | 40% | 30% | 22.5%
SGN INVP7 | Amber | Amber | Red | Red | 4 | 0 | UM | Green | Amber | Amber | Amber | 4 | ◄ | 3 |  | 30% | 22.5% | 22.5%
SGN INVP8 | Red | Red | Red | Red | 6 | 0 |  | Green | Amber | Amber | Amber | 6 | ◄ | 4.5 |  | 30% | 22.5% | 22.5%
SGN INVP9 | Green | Green | Amber | Green | 6 | 5.55 |  | Green | Green | Amber | Green | 6 | ◄ | 5.55 |  | 40% | 22.5% | 30%
SGN INVP10 | Red | Red | Red | Red | 6 | 0 |  | Green | Green | Green | Amber | 6 | ◄ | 5.55 |  | 40% | 30% | 22.5%
SGN INVP11 | Amber | Amber | Red | Red | 6.1051 | 0 | UM | Green | Green | Green | Amber | 6.1051 | ◄ | 5.6472 |  | 40% | 30% | 22.5%
SGN INVP12 | Green | Green | Green | Green | 3.15 | 3.15 |  | Not Evaluated - Green | Not Evaluated - Green | Not Evaluated - Green | Not Evaluated - Green | 3.15 | ◄ | 3.15
SGN INVP13 | Green | Green | Green | Green | 3.0243 | 3.0243 |  | Not Evaluated - Green | Not Evaluated - Green | Not Evaluated - Green | Not Evaluated - Green | 3.0243 | ◄ | 3.0243
SGN INVP14 | Amber | Amber | Red | Red | 0.7875 | 0 | UM | Green | Green | Green | Green | 0.7875 | ◄ | 0.7875 |  | 40% | 30% | 30%
SGN INVP15 | Green | Green | Green | Green | 5 | 5 |  | Not Evaluated - Green | Not Evaluated - Green | Not Evaluated - Green | Not Evaluated - Green | 5 | ◄ | 5
SGN INVP16 | Green | Green | Amber | Amber | 3.75 | 3.1875 |  | Green | Green | Amber | Amber | 3.75 | ◄ | 3.1875 |  | 40% | 22.5% | 22.5%
SGN INVP17 | Green | Green | Green | Green | 1.85 | 1.85 |  | Not Evaluated - Green | Not Evaluated - Green | Not Evaluated - Green | Not Evaluated - Green | 1.85 | ◄ | 1.85
SGN INVP18 | Green | Green | Green | Green | 1.7762 | 1.7762 |  | Not Evaluated - Green | Not Evaluated - Green | Not Evaluated - Green | Not Evaluated - Green | 1.7762 | ◄ | 1.7762

## WWU
| Draft Determination | [6 empty] | Final Determination
New RAG Calc
Project | Justification | Definition | Resource | Cost Assurity | assumed original request | Ex-ante funding | UM |  |  |  |  | Requested |  | Ex-ante funding | UM | Def wtg | Res Wtg | Cost Wtg
WWUPRJ1 | Red | Amber | Red | Red | 0.52 |  |  | Green | Green | Green | Green | 0.14109 | ▼ | 0.14109
WWUPRJ2 | Red | Amber | Red | Red | 0.52 |  |  | Green | Green | Green | Green | 0.15013 | ▼ | 0.15013
WWUPRJ3 | Red | Amber | Red | Red | 0.52 |  |  | Green | Green | Green | Green | 0.41437 | ▼ | 0.41437
WWUPRJ4 | Red | Amber | Red | Red | 0.52 |  |  | Green | Green | Green | Green | 0.26197 | ▼ | 0.26197
WWUPRJ5 | Red | Amber | Red | Red | 0.52 |  |  | Green | Green | Green | Green | 0.18147 | ▼ | 0.18147
WWUPRJ6 | Red | Amber | Red | Red | 0.52 |  |  | Green | Green | Green | Green | 0.16092 | ▼ | 0.16092
WWUPRJ7 | Red | Red | Red | Red | 0 |  |  | Green | Green | Green | Amber | 7.9432 | ▲ | 7.3475 |  | 40% | 30% | 22.5%
WWUPRJ8 | Amber | Amber | Red | Red | 0.4 |  | UM | Green | Green | Green | Green | 0.41427 | ▲ | 0.41427
WWUPRJ9 | Amber | Amber | Red | Red | 1.6 |  | UM | Green | Green | Green | Amber | 1.7511 | ▲ | 1.6198 |  | 40% | 30% | 22.5%
WWUPRJ10 | Red | Amber | Red | Red | 1.11 |  |  | Green | Green | Green | Green | 1.0786 | ▼ | 1.0786 |  | 40% | 30% | 30%
WWUPRJ11 | Red | Red | Red | Red | 0 |  |  | Green | Green | Green | Green | 0.12476 | ▲ | 0.12476
WWUPRJ12 | Red | Red | Red | Red | 1.5 |  |  | Green | Green | Green | Green | 0.3 | ▼ | 0.3
WWUPRJ13 | Red | Red | Red | Red | 0 |  |  | Green | Green | Green | Green | 0.13647 | ▲ | 0.13647
WWUPRJ14 | Red | Red | Red | Red | 0 |  |  | Green | Green | Green | Green | 0.45654 | ▲ | 0.45654
WWUPRJ15 | Red | Red | Red | Red | 0 |  |  | Green | Green | Green | Green | 0.13647 | ▲ | 0.13647
WWUPRJ16 | Red | Amber | Red | Red | 0.7 |  |  | Green | Amber | Amber | Amber | 5.9396 | ▲ | 4.4547 |  | 30% | 22.5% | 22.5%
WWUPRJ17 | Amber | Amber | Red | Red | 0.75 |  | UM | Green | Green | Green | Green | 0.85938 | ▲ | 0.85938
WWUPRJ18 | Red | Red | Red | Red | 0.4375 |  |  | Green | Green | Green | Green | 0.31572 | ▼ | 0.31572
WWUPRJ19 | Red | Red | Red | Red | 0.4375 |  |  | Green | Green | Green | Green | 0.092312 | ▼ | 0.092312
WWUPRJ20 | Red | Red | Red | Red | 0.4375 |  |  | Green | Green | Green | Green | 0.1079 | ▼ | 0.1079
WWUPRJ21 | Red | Red | Red | Red | 1.55 |  |  | Green | Green | Green | Green | 0.3054 | ▼ | 0.3054
WWUPRJ22 | Red | Red | Red | Red | 0.4375 |  |  | Green | Green | Green | Green | 0.19519 | ▼ | 0.19519
WWUPRJ23 | Amber | Amber | Red | Red | 0.5 |  | UM | Green | Green | Green | Green | 0.14726 | ▼ | 0.14726
WWUPRJ24 | Red | Amber | Red | Red | 0.15 |  |  | Green | Green | Green | Green | 0.14294 | ▼ | 0.14294
WWUPRJ25 | Red | Amber | Red | Red | 0.25 |  |  | Green | Green | Green | Green | 0.10257 | ▼ | 0.10257
WWUPRJ26 | Red | Red | Red | Red | 0 |  |  | Green | Green | Green | Green | 0.086658 | ▲ | 0.086658
WWUPRJ27 | Red | Amber | Red | Red | 1.7 |  |  | Green | Green | Green | Green | 0.80436 | ▼ | 0.80436
WWUPRJ28 | Red | Red | Red | Red | 0 |  |  | Green | Green | Green | Green | 0.03856 | ▲ | 0.03856
WWUPRJ29 | Red | Red | Red | Red | 0 |  |  | Green | Green | Green | Green | 0.12669 | ▲ | 0.12669
WWUPRJ30 | Red | Red | Red | Red | 0 |  |  | Green | Green | Green | Green | 0.080242 | ▲ | 0.080242
WWUPRJ31 | Red | Amber | Red | Red | 1.05 |  |  | Green | Green | Green | Green | 0.9525 | ▼ | 0.9525
WWUPRJ32 | Red | Red | Red | Red | 0 |  |  | Green | Green | Green | Green | 0.09484 | ▲ | 0.09484
WWUPRJ33 | Red | Red | Red | Red | 0 |  |  | Green | Green | Green | Green | 0.14724 | ▲ | 0.14724
WWUPRJ34 | Red | Amber | Red | Red | 0.18 |  |  | Green | Green | Green | Green | 0.61411 | ▲ | 0.61411
WWUPRJ35 | Red | Amber | Red | Red | 0.4 |  |  | Green | Green | Green | Green | 0.72 | ▲ | 0.72
WWUPRJ36 | Red | Red | Red | Red | 0 |  |  | Amber | Amber | Amber | Amber | 2.2578 | ▲ | 1.6933 |  | 30% | 22.5% | 22.5%
WWUPRJ37 | Red | Amber | Red | Red | 0.55 |  |  | Green | Amber | Amber | Amber | 2.3874 | ▲ | 1.7906 |  | 30% | 22.5% | 22.5%
WWUPRJ38 | Red | Red | Red | Red | 0 |  |  | Amber | Amber | Amber | Amber | 2.0342 | ▲ | 1.5256 |  | 30% | 22.5% | 22.5%
WWUPRJ39 | Red | Red | Red | Red | 1.2 |  |  | Amber | Amber | Amber | Amber | 3.8648 | ▲ | 2.8986 |  | 30% | 22.5% | 22.5%
WWUPRJ40 | Red | Red | Red | Red | 0 |  |  | Amber | Red | Red | Amber | 1.2145 | ▲ | 0 | UM | 8% | 6% | 22.5%
WWUPRJ41 | Red | Amber | Red | Red | 0.6 |  |  | Green | Green | Green | Green | 0.12539 | ▼ | 0.12539
WWUPRJ42 | Red | Amber | Red | Red | 0.825 |  |  | Green | Green | Green | Green | 0.62408 | ▼ | 0.62408
WWUPRJ43 | Amber | Amber | Red | Red | 0.7 |  | UM | Green | Green | Green | Green | 0.21396 | ▼ | 0.21396
WWUPRJ44 | Red | Red | Red | Red | 0 |  |  | Green | Green | Green | Green | 0.30039 | ▲ | 0.30039
WWUPRJ45 | Red | Amber | Red | Red | 3.25 |  |  | Green | Green | Green | Green | 0.75209 | ▼ | 0.75209
WWUPRJ46 | Red | Red | Red | Red | 0 |  |  | Green | Green | Green | Green | 0.24444 | ▲ | 0.24444

## Summary of Evaluation Criteria
Relative Importance | 40% | 30% | 30% | Binary | 100%
Criteria | Project definition including timing, scale and dependencies | Definition of required Resources | Cost Assurity | Justification for project |  | RAG Dynamic Range | RAG Funding Factor
Green | 3 | 3 | 3 | 1 |  | 3 | 100%
Amber | 2 | 2 | 2 | 1 |  | 2 | 75%
Red | 1 | 1 | 1 | 0 |  | 1 | 20%
Maximum REDs allowed = 0
Colour code
Green | Green RAG Assessment
Amber | Amber RAG Assessment
Red | Red RAG Assessment
Green | RAG Assessment not considered at DD due to inadequate project justification
Amber | RAG Assessment not considered at DD due to inadequate project justification
Red | RAG Assessment not considered at DD due to inadequate project justification
Green | Green RAG Assessment not revised since DD due to no new material
Amber | Amber RAG Assessment not revised since DD due to no new material
Red | Red RAG Assessment not revised since DD due to no new material